## Sheet1
Action Item # | Entry date | Original Due date | Planned date of completion | Actual date of completion | Assignee [ -> others to do the same] | Type | Section | Action | Status A=abandoned C=complete H=on hold P=partial | Disposition
1 | 2009-04-28 |  |  |  | Randy Turner | NEA |  | Randy Turner will try to find other contacts that would be willing to work with the PWG to help deploy NEA health assessment. (Juniper, Symantec, Cisco are suggested candidates.) Is someone willing to sit down with the PWG and “have discussions”?
2 | 2009-04-28 |  | 2009-06-23 |  | Joe Murdock | NAP |  | Joe Murdock will add NAP protocol information to document and update the conformance section.
10 | 2009-04-16 |  |  |  | Brian Smithson | TCG |  | Brian Smithson will investigate whether a formal relationship document can be created between TCG and PWG. He will find out their position on liaison agreements.
12 | 2009-04-29 |  |  |  | Mike Fenelon | NAP |  | Mike Fenelon will coordinate the next opportunity for a discussion with the Microsoft NAP team.
14 | 2009-05-21 |  |  | 2009-06-04 | Brian Smithson | TCG |  | Brian Smithson will communicate the results of the straw poll to the TCG board member responsible for the TCG HCWG. | C
15 | 2009-06-04 |  |  |  | Jerry Thrasher | Attributes |  | Jerry Thrasher will create yet another draft of the Attribute document to include corrections identified at the June 4 teleconference.
16 | 2009-06-04 |  |  |  | Jerry Thrasher | F2F |  | Jerry Thrasher will add the topic of including IDS information in the MFD Semantic Model to the June Plenary meeting.
COMPLETED ITEMS APPEAR BELOW:
3 | 2009-03-26 |  |  | 2009-04-29 | Joe Murdock | NAP |  | Joe Murdock will include sequence diagrams as illustrative examples for the NAP binding document. | C
4 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | NAP Microsoft |  | Dave Whitehead will coordinate with Randy Turner to generate a proposal to Microsoft on proceeding with obtaining NAP information on what they envision would be the content of a profile—including remediation. Need to identify the appropriate point of contact within Microsoft. | C
5 | 2009-03-26 |  |  | 2009-04-16 | Dave Whitehead | NAP |  | Dave Whitehead will attempt to resolve the following issue: Which of the defined transport(s) are required to be supported in order to guarantee a device can attach to the network? MS defines DHCP, 802.1x, IPSec, and VPN and has extended each to add SOH information. So, in an environment where we are attaching wirelessly via 802.1x and receive our IP address from DHCP, what happens if we only support SOH over DHCP (or 802.1x)? Will we attach or fail? | C | This issue has been added to the list of questions to be discussed with the MS NAP team.
6 | 2009-03-26 |  |  | 2009-03-26 | Randy Turner | NEA |  | Randy Turner will send a link to the updated Attributes document to the NEA WG, and solicit their comments. | C
7 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | Attributes Microsoft |  | Dave Whitehead and Randy Turner will compile a set of questions that are intended for Microsoft—and maintain the answers on an ongoing basis for future reference. This list should include the topic of the four SOH attributes: MS-Quarantine-State MS-Machine-Inventory MS-Packet-Info MS-CorrelationId | C
8 | 2009-03-26 |  |  | 2009-05-21 | Ron Nevo, Dave Whitehead | Action items |  | Ron and Dave will maintain an Action Item spreadsheet that assigns unique IDs to each Action Item and retains the resolution history. | C
9 | 2009-04-16 |  |  | 2009-04-29 | All | TCG |  | Everyone will review Steve Hanna’s comments [http://www.pwg.org/hypermail/ids/0242.html] and be prepared for discussion at the next face-to-face meeting. | C
11 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | NEA |  | Dave Whitehead will send a note to Steve Hanna providing the details of the group’s resolutions to his comments. | C
13 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | Telecon |  | Dave Whitehead will announce the next teleconference. | C
x